##  (hidden)
English |  | Deutsch | Français | English | Italiano
Aktuelle Sprache |  | Sprache 1 | Sprache 2 | Sprache 3 | Sprache 4
Aktuell angezeigte Sprache |  | Deutsch | Français | English | Italiano
| 3 |  |  |  |  | 69763
P R O J E C T M A N A G E M E N T |  | P R O J E K T M A N A G E M E N T | G E S T I O N D E P R O J E T S | P R O J E C T M A N A G E M E N T | G E S T I O N E D I P R O G E T T I | 3
Initialisation |  | Intitialisierung | Initialisation | Initialisation | Inizializzazione
Planning |  | Planung | Planification | Planning | Pianificazione | Deutsch
Decision |  | Entscheidung | Décision | Decision | Decisione | Français
Implementation |  | Realisierung | Réalisation | Implementation | Realizzazione | English
Conclusion |  | Abschluss | Finalisation | Conclusion | Conclusione | Italiano
Roadmap |  | Roadmap | Roadmap | Roadmap | Roadmap
Gantt |  | Gantt | Gantt | Gantt | Gantt
Problem analysis |  | Problemanalyse | Analyse du problème | Problem analysis | Analisi del problema
SWOT analysis |  | SWOT-Analyse | Analyse SWOT | SWOT analysis | Analisi SWOT
Budget |  | Budget | Budget | Budget | Budget
Project charter |  | Projektauftrag | Mandat de projet | Project charter | Mandato del progetto
Go/NoGo |  | Go/NoGo | Go/NoGo | Go/NoGo | Go/NoGo
Project team |  | Projektteam | Equipe de projet | Project team | Team del progetto
Rough planning |  | Grobplanung | Planification sommaire | Rough planning | Pianificazione sommaria
Feasibility |  | Machbarkeit | Faisabilité | Feasibility | Fattibilità
Comunication |  | Kommunikation | Communication | Comunication | Redditività
Define sub-projects |  | Teilprojekte definieren | Définir les sous-projets | Define sub-projects | Definire i sottoprogetti
Determine responsibilities |  | Verantwortungen klären | Définir les responsabilités | Determine responsibilities | Definire le responsabilità
Determine interfaces |  | Definition Schnittstellen | Définition des interfaces | Determine interfaces | Definizione delle interfacce
Determine working packages |  | Definition Arbeitspakete | Définition des travaux | Determine working packages | Definizione dei lavori
Risks |  | Risiken | Risques | Risks | Rischi
Detailed planning |  | Detailplanung | Planification détaillée | Detailed planning | Pianificazione dettagliata
Go/NoGo |  | Go/NoGo | Go/NoGo | Go/NoGo | Go/NoGo
Rough concept |  | Grobkonzept | Concept sommaire | Rough concept | Progetto sommario
Go/NoGo rough concept |  | Go/NoGo Grobkonzept | Go/NoGo concept sommaire | Go/NoGo rough concept | Progetto sommario Go/NoGo
Detailed concept |  | Detailkonzept | Concept détaillé | Detailed concept | Progetto dettagliato
Go/NoGo |  | Go/NoGo | Go/NoGo | Go/NoGo | Go/NoGo
Implement detailed concept |  | Detailkonzept umsetzen | Mettre en œuvre le concept détaillé | Implement detailed concept | Attuare il progetto dettagliato
Project monitoring |  | Projektverfolgung | Suivi du projet | Project monitoring | Monitoraggio del progetto
Ensure partial results |  | Teilresultate sichern | Ass. résultats partiels | Ensure partial results | Assicurare i risultati parziali
Update planning activities |  | Planung aktualisieren | Actualiser planification | Update planning activities | Aggiornare la pianificazione
Inform client |  | Auftraggeber informieren | Informer le mandant | Inform client | Informare il committente
Project status |  | Projektstand | Etat du projet | Project status | Stato del progetto
Final report |  | Schlussbericht | Rapport final | Final report | Rapporto finale
Project termination |  | Auflösung des Projektes | Clôture du projet | Project termination | Chiusura del progetto
Ensure results |  | Ergebnisse sicherstellen | Assurer les résultats | Ensure results | Assicurare i risultati
Vision/Story |  | Vision/Story | Vision/Story | Vision/Story | Vision/Story
Concept |  | Konzept | Concept | Concept | Progetto
Status |  | Stand | État | Status | Stato
Final report |  | Schluss-bericht | Rapport final | Final report | Rapporto finale
Gantt |  | Gantt | Gantt | Gantt | Gantt
Your logo: |  | Ihr Logo: | Votre logo: | Your logo: | Vostro logo:
External res. |  | Externe Ress. | Ress. externes | External res. | Ris. esterne
Internal res. |  | Interne Ress. | Ress. internes | Internal res. | Ris. interni
CHF? h? |  | CHF? h? | CHF? h? | CHF? h? | CHF? h?
Public sector |  | Öffentliche Hand | Secteur public | Public sector | Settore pubblico
Rough |  | Grob | Sommaire | Rough | Sommario
Detail |  | Detail | Détail | Detail | Dettaglio
P R O J E C T C H A R T E R |  | P R O J E K T A U F T R A G | M A N D A T D E P R O J E T | P R O J E C T C H A R T E R | M A N D A T O D E L P R O G E T T O
Project number: |  | Projektnummer: | No. de projet : | Project number: | Numero di progetto:
Start: |  | Beginn: | Début: | Start: | Inizio:
Finish: |  | Ende: | Fin: | Finish: | Fine:
Project title: |  | Projektname: | Nom du projet : | Project title: | Nome progetto:
Procuct Owner: |  | Product Owner: | Product Owner : | Procuct Owner: | Procuct Owner:
Scrum Master: |  | Scrum Master: | Scrum Master : | Scrum Master: | Scrum Master:
Department: |  | Abteilung: | Section : | Department: | Reparto:
Modified on: |  | geändert am: | modifié le : | Modified on: | modificato il:
Deputy: |  | StellvertreterIn: | Remplaçant/e : | Deputy: | Sostituto:
Strategic goal: |  | Strategisches Ziel: | Objectif stratégique | Strategic goal: | Obiettivo strategico
What is the vision? What is the story behind this project? Customer Experience? |  | Was ist die Vision? Welche Story steht hinter diesem Projekt? Kundenerlebnis? | Quelle est la vision ? Quelle est l'histoire derrière ce projet ? Expérience client ? | What is the vision? What is the story behind this project? Customer Experience? | Qual è la visione? Qual è la storia dietro questo progetto? Esperienza del cliente?
Project goals |  | Projektziele | Objectifs du projet | Project goals | Obiettivi del progetto
Indicators |  | Indikatoren | Indicateurs | Indicators | Indicatori
Premise / Condition |  | Prämissen / Bedingung | Prémisses / Condition | Premise / Condition | Premesse / Condizione
Budget / Resources / Persons |  | Budget / Ressourcen / Personen | Budget / Ressources / Personnes | Budget / Resources / Persons | Budget / Risorse / Persone
Internal resources |  | Interne Ressourcen | Ressources internes | Internal resources | Risorse interne
Personnel costs |  | Personalaufw.: | Charges de pers. : | Personnel costs | Spese per il personale
Compare detail project team |  | vgl. Detail Projektteam | voir détail "équipe de projet" | Compare detail project team | v. dettaglio “Team del progetto”
Diverse 1: |  | Diverses 1: | Divers 1 : | Diverse 1: | Diversi 1:
Compare project budget (internal) |  | vgl. Detail Projektbudget (intern) | voir détail "budget interne" | Compare project budget (internal) | v. dettaglio “Budget del progetto (interno)”
Diverse 2: |  | Diverses 2: | Divers 2 : | Diverse 2: | Diversi 2:
External resources |  | Externe Ressourcen | Ressources externes | External resources | Risorse esterne
Diverse 1: |  | Diverses 1: | Divers 1 : | Diverse 1: | Diversi 1:
Compare detail project budget (external) |  | vgl. Detail Projektbudget (extern) | voir détail "budget externe" | Compare detail project budget (external) | v. dettaglio “Budget del progetto (esterno)”
Diverse 2: |  | Diverses 2: | Divers 2 : | Diverse 2: | Diversi 2:
Diverse 3: |  | Diverses 3: | Divers 3 : | Diverse 3: | Diversi 3:
TOTAL RESOURCES |  | TOTAL RESSOURCEN | TOTAL RESSOURCES | TOTAL RESOURCES | TOTALE RISORSE
Deadlines / Milestones (Go/NoGo) |  | Termine/Meilensteine (Go/NoGo) | Délais / Jalon (Go/NoGo) | Deadlines / Milestones (Go/NoGo) | Scadenze / Pietre miliari (Go/NoGo)
When? |  | Wann? | Quand? | When? | Quando?
What? |  | Was? | Quoi? | What? | Che cosa?
Who? |  | Wer? | Qui? | Who? | Chi?
Approved? |  | Genehmigt? | Approuvé? | Approved? | Approvato?
Remarks / attachments |  | Bemerkungen/Beilagen | Commentaires/pièces jointes | Remarks / attachments | Osservazioni/Allegati
Discuss project charter and have it signed by client |  | Projektauftrag besprechen und von AuftraggeberIn unterschreiben | Discuter du mandat et le faire signer par le mandant | Discuss project charter and have it signed by client | Discutere il mandato e farlo firmare dal committente
Detailed planning drawn up and Go/NoGo from client |  | Detailplan erstellt und Go/No Go von AuftraggeberIn | Plan détaillé établi et Go/No Go de la part du mandant | Detailed planning drawn up and Go/NoGo from client | Allestita la pianificazione dettagliata e Go/No Go del committente
Rough concept drawn up and Go/NoGo from client |  | Grobkonzept erstellt und Go/No Go von AuftraggeberIn | Concept général établi et Go/No Go de la part du mandant | Rough concept drawn up and Go/NoGo from client | Allestito il progetto sommario e Go/No Go del/della committente
Detailed concept drawn up and Go/NoGo from client |  | Detailkonzept erstellt und Go/No Go von AuftraggeberIn | Concept détaillé établi et Go/No Go de la part du mandant | Detailed concept drawn up and Go/NoGo from client | Allestito il progetto dettagliato e Go/No Go del/della committente
Monthly interim report to client |  | Monatlicher Zwischenrapport an AuftraggeberIn | Rapport intermédiaire mensuel à l'attention du mandant | Monthly interim report to client | Rapporto intermedio mensile all’attenzione del/della committente
Final report to client |  | Schlussrapport an AuftraggeberIn | Rapport final à l'attention du mandant | Final report to client | Rapporto finale all’attenzione del/della committente
Date |  | Datum | Date | Date | Data
Client signature |  | Unterschrift AuftraggeberIn | Signature mandant | Client signature | Firma del/della committente
Project manager signature |  | Unterschrift ProjektleiterIn | Signature chef de projet | Project manager signature | Firma del/della responsabile di progetto
Vision Scope |  | Vision Ziele | Vision Objectifs | Vision Scope | Visione Obiettivi
Product Backlog |  | Produkt-Backlog | Backlog produit | Product Backlog | Backlog prodotto
Sprint Planning |  | Sprint-Planung | Planif sprint | Sprint Planning | Pianif sprint
ITERATION |  | ITERATION | ITERATION | ITERATION | ITERAZIONE
Sprint Review |  | Sprint Review | Revue Sprint | Sprint Review | Revisione Sprint
1-4 Weeks |  | 1-4 Wochen | 1-4 semaines | 1-4 Weeks | 1-4 settimane
DAILY SCRUM |  | DAILY SCRUM | SCRUM QUOTIDIEN | DAILY SCRUM | DAILY SCRUM
Sprint Retrospective |  | Sprint-Retrospektive | Rétrospective sprint | Sprint Retrospective | Retrospettiva sprint
Product Increment |  | Produkt-Inkrement | Incrément du produit | Product Increment | Incremento del prodotto
Story points |  | Story points | Story points | Story points | Story points
Sprint |  | Sprint | Sprint | Sprint | Sprint
Stage |  | Etappe | Étape | Stage | Fase
Not started |  | Nicht gestartet | Pas commencé | Not started | Non iniziato
In progress |  | In Arbeit | En cours | In progress | In corso
Stopped |  | Gestoppt | Suspendu | Stopped | Sospeso
Testing |  | Im Test | En test | Testing | In test
Completed |  | Abgeschlossen | Terminé | Completed | Completato
Accepted |  | Angenommen | Accépté | Accepted | Accettato
Sprint Backlog |  | Sprint-Backlog | Backlog sprint | Sprint Backlog | Backlog sprint
[h] |  | [h] | [h] | [h] | [h]
Points |  | Punkte | Points | Points | Punti
0
Product Backlog |  | Produkt-Backlog | Backlog produit | Product Backlog | Backlog prodotto
Sort |  | Sortieren | Trier | Sort | Selezionare
Today |  | Heute | Aujourd'hui | Today | Oggi
Story |  | Story | Story | Story | Story
Yes |  | Ja | Oui | Yes | Sì
Responsible |  | Zust. | Resp. | Responsible | Resp.
Filter: |  | Filter: | Filtre : | Filter: | Filtro:
Total hours |  | Total Stunden | Totale heures | Total hours | Totale ore
Total realized [h] |  | Total realisiert [h] | Total réalisées [h] | Total realized [h] | Totale realizzati [h]
Budget [h] |  | Budget [h] | Budget [h] | Budget [h] | Budget [h]
Budget [CHF] |  | Budget [CHF] | Budget [CHF] | Budget [CHF] | Budget [CHF]
intern: |  | intern: | interne : | intern: | interno:
extern: |  | extern: | externe : | extern: | esterno:
Balance budget [h] |  | Saldo Budget [h] | Solde budget [h] | Balance budget [h] | Saldo budget [h]
Balance budget [CHF] |  | Saldo Budget [CHF] | Solde budget [CHF] | Balance budget [CHF] | Saldo budget [CHF]
Balance [%] |  | Saldo [%] | Solde [%] | Balance [%] | Saldo [%]
Balance |  | Saldo | Solde | Balance | Saldo
Realized |  | Realisiert | Réalisées | Realized | Realizzati
Balance realized days |  | Saldo realisierte Tage | Solde jours réalisées | Balance realized days | Saldo giorni realizzati
days |  | Tage | jours | days | giorni
hours |  | Stunden | heures | hours | ore
Overview of the hours |  | Übersicht der Stunden | Aperçu des heures | Overview of the hours | Panoramica delle ore
Period (days) |  | Dauer (Tage) | Durée (jours) | Period (days) | Durata (giorni)
Balance |  | Saldo | Solde | Balance | Saldo
Total |  | Total | Total | Total | Totale
No. |  | Nr. | No. | No. | No.
Date |  | Datum | Date | Date | Data
EPIC |  | EPIC | EPIC | EPIC | EPIC
Priority |  | Priorität | Priorité | Priority | Priorità
Progress |  | Fortschritt | Progression | Progress | Progresso
0
Sprint Backlog |  | Sprint-Backlog | Backlog sprint | Sprint Backlog | Backlog sprint
Sprint activities |  | Sprint Aktivitäten | Activités sprint | Sprint activities | Attività sprint
Release |  | Release | Release | Release | Release
Budget [h] |  | Budget [h] | Budget [h] | Budget [h] | Budget [h]
Overall sprint |  | Sprint insgesamt | Sprint général | Overall sprint | Sprint generale
Sprint goals |  | Sprint-Ziele | Objectifs du sprint | Sprint goals | Obiettivi dello sprint
To Do |  | To Do | To Do | To Do | To Do
In progress |  | In Arbeit | En cours | In progress | In corso
Accomplished |  | Erledigt | Terminé | Accomplished | Fatto
Target |  | Ziele | Objectifs | Target | Objettivi
Budget |  | Budget | Budget | Budget | Budget
Is the (partial) product successful? |  | Ist das (Teil-)Produkt erfolgreich? | Le produit (partiel) est-il un succès ? | Is the (partial) product successful? | Il prodotto (parziale) ha successo?
Remarks/Lessons Learned |  | Bemerkungen/Lessons Learned | Commentaires/Lessons Learned | Remarks/Lessons Learned | Osservazioni/Lessons Learned
0
0
0
0
R O U G H P L A N N I N G |  | P L A N U N G Ü B E R S I C H T | P L A N I F I C A T I O N S O M M A I R E | R O U G H P L A N N I N G | P I A N I F I C A Z I O N E S O M M A R I O
done |  | erledigt | terminé | done | fatto
in progress |  | in Arbeit | en cours | in progress | in corso
milestones |  | Meilensteine | jalons | milestones | pietre miliari
P R O J E C T S T A T U S |  | P R O J E K T S T A N D | E T A T D U P R O J E T | P R O J E C T S T A T U S | S T A T O D E L P R O G E T T O
General Evaluation (1 = proceeding according to plan, 2 = be watchful = 3 critical) |  | Allgemeine Beurteilung (1 = läuft planmässig; 2 = im Auge behalten; 3 = kritisch) | Evaluation générale (1 = se déroule comme prévu ; 2 = à surveiller ; 3 = critique) | General Evaluation (1 = proceeding according to plan, 2 = be watchful = 3 critical) | Valutazione generale (1 = si svolge come previsto; 2 = da tenere sotto controllo; 3 = critico)
Overall project |  | Gesamtprojekt | Projet global | Overall project | Progetto globale
Budget/Resources |  | Budget/Ressourcen | Budget/Ressources | Budget/Resources | Budget/Risorse
Quality/Goals |  | Qualität/Ziele | Qualité/Objectifs | Quality/Goals | Qualità/Obiettivi
Deadlines/Planning |  | Termine/Planung | Délais/Planification | Deadlines/Planning | Scadenze/Pianificaz.
Proceeding according to plan |  | läuft planmässig | comme prévu | Proceeding according to plan | Si svolge come previsto
Critical |  | kritisch | critique | Critical | Critico
Be watchful |  | im Auge behalten | à surveiller | Be watchful | Da tenere sotto controllo
According to plan |  | läuft planmässig | comme prévu | According to plan | Si svolge come previsto
Remarks |  | Bemerkungen | Commentaires | Remarks | Osservazioni
Achievements (last period) |  | Erfolge (letzte Periode) | Succès (dernière période) | Achievements (last period) | Successi (ultimo periodo)
Particular problems (last period) |  | Besondere Probleme (letzte Periode) | Problèmes spécifiques (dernière période) | Particular problems (last period) | Problemi particolari (ultimo periodo)
Challenges (next period) |  | Herausforderungen (nächste Periode) | Défis (prochaine période) | Challenges (next period) | Sfide (prossimo periodo)
PLAN |  | PLAN | PLAN | PLAN | PIANIFICAZIONE
ACTUAL STATE |  | IST | RÉEL | ACTUAL STATE | SITUAZIONE REALE
BALANCE |  | SALDO | SOLDE | BALANCE | SALDO
In % |  | in % | en % | In % | In %
see charter |  | siehe Auftrag | Voir mandat | see charter | vedere mandato
Project goals (see charter) |  | Projektziele (vgl. Projektauftrag) | Objectifs du projet (cf. mandat) | Project goals (see charter) | Obiettivi del progetto (vedere mandato)
Next milestone: |  | Nächster Meilenstein: | Prochain jalon : | Next milestone: | Prossima pietra miliar.:
F I N A L R E P O R T |  | S C H L U S S B E R I C H T | R A P P O R T F I N A L | F I N A L R E P O R T | R A P P O R T O F I N A LE
Was the project successful? |  | War das Projekt erfolgreich? | Projet couronné de succès ? | Was the project successful? | Il progetto ha avuto esito positivo?
Yes |  | ja | oui | Yes | Sì
Reason: |  | Begründung: | Justification: | Reason: | Motivazione:
Are all customer needs satisfied? |  | Sind alle Kundenbedürfnisse befriedigt? | Tous les besoins des clients sont-ils satisfaits ? | Are all customer needs satisfied? | Tutte le esigenze dei clienti sono soddisfatte?
Partially |  | teilweise | partiellement | Partially | In parte
Was the budget observed? |  | Wurde das Budget eingehalten? | Le budget a-t-il été respecté ? | Was the budget observed? | Il budget è stato rispettato?
No |  | nein | non | No | No
Further comments |  | Weitere Bemerkungen | Autres remarques | Further comments | Altri commenti
What can be learnt from the project? (Lessons Learned) |  | Was kann aus dem Projekt gelernt werden? (Lessons Learned) | Quels sont les enseignements tirés du projet ? (Lessons Learned) | What can be learnt from the project? (Lessons Learned) | Quali insegnamenti è possibile trarre dal progetto? (Lessons Learned)
P R O J E C T T E A M |  | P R O J E K T T E A M | E Q U I P E D E P R O J E T | P R O J E C T T E A M | T E A M D E L P R O G E T T O
Name |  | Name | Nom | Name | Cognome
First name |  | Vorname | Prénom | First name | Nome
Initials |  | Kürzel | Abrév. | Initials | Sigla
intern |  | intern | interne | intern | interno
Email |  | e-mail | e-mail | Email | Mail
Telephone |  | Telefon | Téléphone | Telephone | Telefono
Hourly rate |  | Stundenansatz | Tarif horaire | Hourly rate | Tariffa oraria
BUDGET |  | BUDGET | BUDGET | BUDGET | BUDGET
hours budget |  | Budget Stunden | heures budget | hours budget | ore budget
allocated hours |  | zugeordnete Stunden | heures attribuées | allocated hours | ore attribuite
realized hours |  | realisierte Stunden | heures réalisées | realized hours | ore realizzate
[CHF] |  | [CHF] | [CHF] | [CHF] | [CHF]
Absence/Remarks |  | Absenzen/Bemerkungen | Absences/Remarques | Absence/Remarks | Assenze/Osservazioni
Total intern |  | Total intern | Total interne | Total intern | Totale interno
Total extern |  | Total extern | Total externe | Total extern | Totale esterno
TOTAL |  | TOTAL | TOTAL | TOTAL | TOTALE
Function |  | Funktion | Fonction | Function | Funzione
BALANCE [CHF] |  | SALDO [CHF] | SOLDE [CHF] | BALANCE [CHF] | SALDO [CHF]
BALANCE |  | SALDO | SOLDE | BALANCE | SALDO
Budget [h] |  | Budget [h] | budget [h] | Budget [h] | Budget [h]
realized [h] |  | realisiert [h] | réalisées [h] | realized [h] | realizzate [h]
balance budget [h] |  | Saldo Budget [h] | solde budget [h] | balance budget [h] | saldo budget [h]
B U D G E T |  | B U D G E T | B U D G E T | B U D G E T | B U D G E T
Internal resources |  | Interne Ressourcen | Ressources internes | Internal resources | Risorse interni
Title |  | Bezeichnung | Libellé | Title | Titolo
Standard price |  | Einheitspreis | Prix unitaire | Standard price | Prezzo unitario
Amount |  | Anz. | Nb. | Amount | Quant.
Costs (internal) |  | Ressourcen (intern) | Coûts (internes) | Costs (internal) | Costi (interni)
Remarks |  | Bemerkungen | Remarques | Remarks | Osservazioni
External resources |  | Externe Ressourcen | Ressources externes | External resources | Risorse esterne
Resources (external) |  | Ressourcen (extern) | Ressources (externes) | Resources (external) | Risorse (esterni)
External financing |  | Externe Finanzierung | Financement externe | External financing | Finanziamento esterno
External financing (eg customers, subsidies etc.) |  | Externe Finanzierung (z.B. Kunden, Subventionen etc.) | Financement externe (p.ex. clients, subventions etc.) | External financing (eg customers, subsidies etc.) | Finanziamento esterno (a.e. Clienti, sussidi ecc)
TOTAL external resources |  | TOTAL externe Ressourcen | TOTAL ressources externes | TOTAL external resources | TOTALE risorse esternr
TOTAL internal resources |  | TOTAL interne Ressourcen | TOTAL ressources internes | TOTAL internal resources | TOTALE risorse internr
TOTAL external finances |  | TOTAL externe Finanzierung | TOTAL financement externe | TOTAL external finances | TOTALE finanzamenti esterni
Personnel resources (internal) |  | Personalressourcen (intern) | Charges de personnel (internes) | Personnel resources (internal) | Spese per il personale (interni)
Personnel resources (external) |  | Personalressourcen (extern) | Charges de personnel (externes) | Personnel resources (external) | Spese per il personale (esterni)
TOTAL RESOURCES |  | TOTAL RESSOURCEN | TOTAL RESSOURCES | TOTAL RESOURCES | TOTALE RISORSE
Plan |  | Plan | Plan | Plan | Pianificazione
Actual state |  | Ist | Réel | Actual state | Reale
Balance |  | Saldo | Solde | Balance | Saldo
E R R O R M E S S A G E S |  | Fehlermeldungen | Messages d'erreurs | E R R O R M E S S A G E S | Messaggi di errore
Please fill in date of project start in project charter!! |  | Bitte Datum des Projektbeginns im Auftrag eingeben!! | Veuillez s.v.p. saisir la date du début du projet dans le mandat!! | Please fill in date of project start in project charter!! | Si prega di immettere la data dell’inizio del progetto nel mandato!
Finish |  | Ende | Fin | Finish | Fine
S W O T A N A L Y S I S |  | S W O T - A N A L Y S E | A N A L Y S E S W O T | S W O T A N A L Y S I S | A N A L I S I S W O T
Strength |  | Stärken | Forces | Strength | Forze
Weaknesses |  | Schwächen | Faiblesses | Weaknesses | Lacune
Opportunities |  | Chancen | Opportunités | Opportunities | Opportunità
Threats |  | Gefahren | Menaces | Threats | Minacce
R I S K A N A L Y S I S |  | R I S I K O A N A L Y S E | A N A L Y S E D U R I S Q U E | R I S K A N A L Y S I S | A N A L I S I D E L R I S C H I O
Probability of occurrence |  | Eintretenswahrscheinlichkeit | Probabilité d'occurrence | Probability of occurrence | Probabilità di occorrenza
High |  | hoch | élevée | High | Elevata
Medium |  | mittel | moyenne | Medium | Media
Low |  | gering | faible | Low | Bassa
Extent of damage |  | Schadensausmass | Étendue des dégâts | Extent of damage | Entità dei danni
No need for action |  | Kein Handlungsbedarf | Aucune action nécessaire | No need for action | Nessun intervento necessario
Need for action |  | Handlungsbedarf | Action nécessaire | Need for action | Intervento necessario
Urgent need for action |  | Akuter Handlungsbedarf | Action urgente | Urgent need for action | Intervento urgente
No. |  | Nr. | No. | No. | N°
Risk |  | Risiko | Risque | Risk | Rischio
Consequences |  | Auswirkungen | Impact | Consequences | Effetti
Probability of occurrence |  | Eintretens-wahrscheinlich-keit | Probabilité d'occurrence | Probability of occurrence | Probabilità di occorrenza
Extent of damage |  | Schadens-ausmass | Étendue des dommages | Extent of damage | Entità dei danni
Ten-dency |  | Trend | Ten- dance | Ten-dency | Ten- denza
Possible measures |  | Mögliche Massnahmen | Mesures possibles | Possible measures | Provvedimenti possibili
Status |  | Status | Statut | Status | Status
Extent of consequences |  | Ausmass der Auswirkungen | Étendue de l'impact | Extent of consequences | Entità degli effetti
F E A S I B I L I T Y |  | M A C H B A R K E I T | F A I S A B I L I T É | F E A S I B I L I T Y | F A T T I B I L I T À
Organizational feasibility |  | Organisatorische Machbarkeit | Faisabilité organisationnelle | Organizational feasibility | Fattibilità organizzativa
Economic feasibility |  | Wirtschaftliche Machbarkeit | Faisabilité économique | Economic feasibility | Fattibilità economica
Technical feasibility |  | Technische Machbarkeit | Faisabilité technique | Technical feasibility | Fattibilità tecnica
Resources and time |  | Ressourcen und Zeit | Ressources et temps | Resources and time | Risorse e tempo
Legal feasibility |  | Rechtliche Machbarkeit | Faisabilité juridique | Legal feasibility | Fattibilità giuridica
No. |  | Nr. | No. | No. | N°
Title |  | Bezeichnung | Désignation | Title | Nome
Consequences |  | Auswirkungen | Impact | Consequences | Effetti
Degree of danger |  | Gefahren-grad | Degré de danger | Degree of danger | Grado di pericolo
Influence on the project |  | Einfluss auf das Projekt | Impact sur le projet | Influence on the project | Impatto sul progetto
Ten-dency |  | Trend | Ten- dance | Ten-dency | Ten- denza
Possible measures |  | Mögliche Massnahmen | Mesures possibles | Possible measures | Provvedimenti possibili
Status |  | Status | Statut | Status | Status
Average |  | Durchschnitt | Moyenne | Average | Media
Sum |  | Summe | Somme | Sum | Somma
Feasibility |  | Machbarkeit | Faisabilité | Feasibility | Fattibilità
P R O J E C T C O N T R O L L I N G |  | P R O J E K T C O N T R O L L I N G | C O N T R O L L I N G P R O J E T S | P R O J E C T C O N T R O L L I N G | C O N T R O L L I N G P R O G E T T I
No. |  | Nr. | No. | No. | N°
Projects |  | Projekte | Projets | Projects | Progetti
Start |  | Beginn | Début | Start | Inizio
Finish |  | Ende | Fin | Finish | Fine
Who? |  | Wer? | Qui ? | Who? | Chi?
Remarks |  | Bemerkungen | Commentaires | Remarks | Osservazioni
Calendar |  | Kalender | Calendrier | Calendar | Calendario
Su |  | So | Di | Su | Do
Mo |  | Mo | Lu | Mo | Lu
Tu |  | Di | Ma | Tu | Ma
We |  | Mi | Me | We | Me
Th |  | Do | Je | Th | Gio
Fr |  | Fr | Ve | Fr | Ve
Sa |  | Sa | Sa | Sa | Sa
C O M M U N I C A T I O N |  | K O M M U N I K A T I O N | C O M M U N I C A T I O N | C O M M U N I C A T I O N | COMUNICAZIONE
Goals |  | Ziele | Objectifs | Goals | Obiettivi
Periodicity |  | Periodizität | Périodicité | Periodicity | Periodicità
Internet |  | Internet | Internet | Internet | Internet
Social Media |  | Social Medias | Social Medias | Social Media | Social media
Public relations |  | Public Relations | Relations publiques | Public relations | Pubbliche relazioni
Diverse |  | Diverses | Divers | Diverse | Varie
Impact |  | Impact | Impact | Impact | Impatto
No. |  | Nr. | No. | No. | N.
Target public |  | Zielpublikum | Public cible | Target public | Pubblico target
In % |  | in % | en % | In % | in %
Key Message |  | Kernbotschaft | Message clé | Key Message | Messaggio chiave
Indicators |  | Indikatoren | Indicateurs | Indicators | Indicatori
Priority |  | Prioriät | Priorité | Priority | Priorità
Remarks |  | Bemerkungen | Remarques | Remarks | Osservazioni
Who? |  | Wer? | Qui ? | Who? | Chi?
Channel |  | Kanal | Canal | Channel | Canale
Target |  | SOLL | DOIT | Target | STATO DESIDERATO
achieved |  | erreicht | atteint | achieved | raggiunto
Mon |  | Mo | Lun | Mon | Lu
Tue |  | Di | Mar | Tue | Ma
Wed |  | Mi | Mer | Wed | Me
Thu |  | Do | Jeu | Thu | Gio
Fri |  | Fr | Ven | Fri | Ve
Sat |  | Sa | Sam | Sat | Sa
Overview Meetings |  | Übersicht Sitzungen | Aperçu des séances | Overview Meetings | Panoramica sedute
Date |  | Datum | Date | Date | Data
Links documents |  | Links zu Dokumenten | Liens vers les documents | Links documents | Link a documenti
Important decisions / Remarks |  | Wichtigsten Entscheide / Bemerkungen | Décisions les plus importantes / Remarques | Important decisions / Remarks | Le decisioni più importanti / Osservazioni
Protocol of modifications |  | Änderungsprotokoll | Suivi des modifications | Protocol of modifications | Monitoraggio delle modifiche
Date |  | Datum | Date | Date | Data
Modifications |  | Änderungen | Changement | Modifications | Modifiche
Who? |  | Wer? | Qui? | Who? | Chi?
0
S T A K E H O L D E R |  | S T A K E H O L D E R | P A R T I E S P R E N A N T E S | S T A K E H O L D E R | S T A K E H O L D E R
Wider environment |  | weites Umfeld | Contexte large | Wider environment | Contesto ampio
Immediate environment |  | nahes Umfeld | Contexte restreint | Immediate environment | Contesto ristretto
Internal |  | intern | interne | Internal | interno
Us |  | Wir | Nous | Us | Noi
Frequent contacts |  | häufiger Kontakt | contacts fréquents | Frequent contacts | Contatti frequenti
Regular contacts |  | regelmässiger Kontakt | contacts réguliers | Regular contacts | Contatti regolari
Rare contacts |  | seltener Kontakt | contacts rares | Rare contacts | Contatti rari
High |  | hoch | grande | High | alto
Big |  | gross | grand | Big | grande
Stakeholder influence |  | Einfluss der Stakeholder | Influence des parties prenantes | Stakeholder influence | Influsso degli stakeholder
Low |  | gering | petite | Low | basso
Small |  | klein | petit | Small | piccolo
Stakeholder interest |  | Interesse der Stakeholder | Intérêt des parties prenantes | Stakeholder interest | Interesse degli stakeholder
No. |  | Nr. | No. | No. | N.
Stakeholder |  | Anspruchsgruppe | Parties prenantes | Stakeholder | Stakeholder
Interests, expectations |  | Interessen, Erwartungen | Intérêt, attentes | Interests, expectations | Interessi, attese
Extent of interests |  | Stärke der Interessen | Etendue de l'intérêt | Extent of interests | Intensità degli interessi
Degree of influence |  | Höhe des Einflusses | Etendue de l'influence | Degree of influence | Intensità dell'influsso
Chances (+) and dangers (-) |  | Chancen (+) und Gefahren (-) | Chances (+) et Dangers (-) | Chances (+) and dangers (-) | Opportunità (+) e pericoli (-)
Possible measures |  | Mögliche Massnahmen | Mesures possibles | Possible measures | Misure possibili
Status |  | Status | Statut | Status | Statuto
Size of group |  | Grösse der Gruppe | Taille du groupe | Size of group | Dimensioni del gruppo
S T A K E H O L D E R A N A L Y S I S |  | S T A K E H O L D E R - A N A L Y S E | A N A L Y S E D E S P A R T I E S P R E N A N T E S | S T A K E H O L D E R A N A L Y S I S | A N A L I S I D E G L I S T A K E H O L D E R
Keep satisfied |  | Zufrieden halten | Maintenir satisfait | Keep satisfied | mantenere soddisfatto
Monitor |  | Beobachten | Surveiller | Monitor | monitorare
Keep informed |  | Informiert halten | Tenir informé | Keep informed | tenere informati
Manage closely |  | Intensive Betreuung | Suivre de près | Manage closely | gestire strettamente
Copy arrow: ctrl and left mouse button |  | Pfeil kopieren: ctrl und linke Maustaste | Copier flèche: ctrl et bouton gauche de la souris | Copy arrow: ctrl and left mouse button | Copia freccia: ctrl e pulsante sinistro del mouse
Links |  | Links | Liens | Links | Links
Would you like to download a new file? |  | Möchten Sie eine neue Datei herunterladen? | Voulez-vous télécharger un nouveau fichier ? | Would you like to download a new file? | Volete scaricare un nuovo file?
Please make sure that you have an internet connection! |  | Stellen Sie sicher, dass ein Internetzugang besteht! | Assurez-vous, que vous avez une connexion internet! | Please make sure that you have an internet connection! | Assicurarsi di avere una connessione internet!
Remark: |  | Bemerkung: | Remarque : | Remark: | Osservazione:
On iMangement you can download the latest version. |  | Sie können auf iMangement jeweils die neuste Version herunterladen. | Sur iMangement vous pouvez télécharger la dernière version. | On iMangement you can download the latest version. | Su iMangement è possibile scaricare la versione più recente.
Currency: |  | Währung: | Devise: | Currency: | Moneta:
yes |  | ja | oui | yes | si
no |  | nein | non | no | no
green |  | grün | vert | green | verde
orange |  | orange | orange | orange | arrancio
red |  | rot | rouge | red | rosso
Question |  | Frage | Question | Question | Questione
Answer |  | Antwort | Réponse | Answer | Risposta
Roadmap |  | Roadmap | Feuille de route | Roadmap | Tabella di marcia
Steps |  | Phasen | Étapes | Steps | Fasi
Goals |  | Ziele | Objectifs | Goals | Obiettivi
Activities |  | Aktivitäten | Activités | Activities | Attività
Deliverables |  | Ergebnisse | Livrables | Deliverables | Deliverables
Timeline |  | Fristen | Échéance | Timeline | Scadenza
0
Start |  | Beginn | Début | Start | Inizio
Finish |  | Ende | Fin | Finish | Fine
Who? |  | Wer? | Qui ? | Who? | Chi?
Agile Manifesto |  | Agiles Manifest | Manifeste agile | Agile Manifesto | Manifesto Agile
We are uncovering better ways of developing software by doing it and helping others do it. Through this work we have come to value: |  | Wir erschließen bessere Wege, Software zu entwickeln, indem wir es selbst tun und anderen dabei helfen. Durch diese Tätigkeit haben wir diese Werte zu schätzen gelernt: | Nous découvrons de meilleures approches du développement logiciel en le pratiquant et en aidant les autres à le pratiquer. Ce travail nous a amené à accorder de l'importance : | We are uncovering better ways of developing software by doing it and helping others do it. Through this work we have come to value: | Stiamo scoprendo modi migliori di sviluppare software facendolo e aiutando gli altri a farlo. Attraverso questo lavoro siamo arrivati ad apprezzare:
Individuals and interactions |  | Individuen und Interaktionen | aux individus et leurs interactions | Individuals and interactions | Gli individui e le interazioni
over processes and tools |  | sind wichtiger als Prozesse und Werkzeuge | plutôt qu'aux processus et aux outils | over processes and tools | più che i processi e gli strumenti
Working software |  | Funktionierende Software | à un logiciel fonctionnel | Working software | Il software funzionante
over comprehensive documentation |  | ist wichtiger als umfassende Dokumentationen | plutôt qu’à une documentation exhaustive | over comprehensive documentation | più che la documentazione esaustiva
Customer collaboration |  | Zusammenarbeit mit dem Kunden | à la collaboration avec les clients | Customer collaboration | La collaborazione col cliente
over contract negotiation |  | ist wichtiger als Vertragsverhandlungen | plutôt qu'à la négociation contractuelle | over contract negotiation | più che la negoziazione dei contratti
Responding to change |  | Reagieren auf Veränderung | à l’adaptation au changement | Responding to change | Rispondere al cambiamento
over following a plan |  | ist wichtiger als das Befolgen eines Plans | plutôt qu'à l'exécution d’un plan | over following a plan | più che seguire un piano
That is, while there is value in the items on the right, we value the items on the left more. |  | Das heißt, obwohl wir die Werte auf der rechten Seite wichtig finden, schätzen wir die Werte auf der linken Seite höher ein. | Cela signifie que, bien qu'il y ait de la valeur dans les éléments situés à la fin, notre préférence se porte sur les éléments qui se trouvent en première partie de phrase. | That is, while there is value in the items on the right, we value the items on the left more. | Ovvero, fermo restando il valore delle voci a destra, si considerano più importanti le voci a sinistra.
Our highest priority is to satisfy the customer through early and continuous delivery of valuable software. |  | Unsere höchste Priorität ist es, den Kunden durch frühe und kontinuierliche Auslieferung wertvoller Software zufrieden zu stellen. | Notre plus haute priorité est de satisfaire le client en livrant rapidement et régulièrement des fonctionnalités à grande valeur ajoutée. | Our highest priority is to satisfy the customer through early and continuous delivery of valuable software. | La nostra massima priorità è soddisfare il cliente attraverso la consegna rapida e continua di software di valore.
Welcome changing requirements, even late in development. Agile processes harness change for the customer’s competitive advantage. |  | Heiße Anforderungsänderungen selbst spät in der Entwicklung willkommen. Agile Prozesse nutzen Veränderungen zum Wettbewerbsvorteil des Kunden. | Accueillez positivement les changements de besoins, même tard dans le projet. Les processus Agiles exploitent le changement pour donner un avantage compétitif au client. | Welcome changing requirements, even late in development. Agile processes harness change for the customer’s competitive advantage. | Accogliere i requisiti che cambiano, anche in ritardo nello sviluppo. I processi agili sfruttano il cambiamento per il vantaggio competitivo del cliente.
Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale. |  | Liefere funktionierende Software regelmäßig innerhalb weniger Wochen oder Monate und bevorzuge dabei die kürzere Zeitspanne. | Livrez fréquemment un logiciel fonctionnel, dans des cycles de quelques semaines à quelques mois, avec une préférence pour les plus courts. | Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale. | Consegnare software funzionante frequentemente, da un paio di settimane a un paio di mesi, con una preferenza per i tempi più brevi.
Business people and developers must work together daily throughout the project. |  | Fachexperten und Entwickler müssen während des Projektes täglich zusammenarbeiten. | Les utilisateurs ou leurs représentants et les développeurs doivent travailler ensemble quotidiennement tout au long du projet. | Business people and developers must work together daily throughout the project. | Gli uomini d'affari e gli sviluppatori devono lavorare insieme ogni giorno durante il progetto.
Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done. |  | Errichte Projekte rund um motivierte Individuen. Gib ihnen das Umfeld und die Unterstützung, die sie benötigen und vertraue darauf, dass sie die Aufgabe erledigen. | Réalisez les projets avec des personnes motivées. Fournissez-leur l’environnement et le soutien dont elles ont besoin et faites-leur confiance pour atteindre les objectifs fixés. | Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done. | Costruire i progetti intorno ad individui motivati. Date loro l'ambiente e il supporto di cui hanno bisogno, e fidatevi di loro per portare a termine il lavoro.
The most efficient and effective method of conveying information to and within a development team is face-to-face conversation. |  | Die effizienteste und effektivste Methode, Informationen an und innerhalb eines Entwicklungsteams zu übermitteln, ist im Gespräch von Angesicht zu Angesicht. | La méthode la plus simple et la plus efficace pour transmettre de l’information à l'équipe de développement et à l’intérieur de celle-ci est le dialogue en face à face. | The most efficient and effective method of conveying information to and within a development team is face-to-face conversation. | Il metodo più efficiente ed efficace per trasmettere informazioni a e all'interno di un team di sviluppo è la conversazione faccia a faccia.
Working software is the primary measure of progress. |  | Funktionierende Software ist das wichtigste Fortschrittsmaß. | Un logiciel fonctionnel est la principale mesure de progression d'un projet. | Working software is the primary measure of progress. | Il software funzionante è la misura primaria del progresso.
Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely. |  | Agile Prozesse fördern nachhaltige Entwicklung. Die Auftraggeber, Entwickler und Benutzer sollten ein gleichmäßiges Tempo auf unbegrenzte Zeit halten können. | Les processus agiles encouragent un rythme de développement soutenable. Ensemble, les commanditaires, les développeurs et les utilisateurs devraient être capables de maintenir indéfiniment un rythme constant. | Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely. | I processi agili promuovono lo sviluppo sostenibile. Gli sponsor, gli sviluppatori e gli utenti dovrebbero essere in grado di mantenere un ritmo costante indefinitamente.
Continuous attention to technical excellence and good design enhances agility. |  | Ständiges Augenmerk auf technische Exzellenz und gutes Design fördert Agilität. | Une attention continue à l'excellence technique et à un bon design. | Continuous attention to technical excellence and good design enhances agility. | L'attenzione continua all'eccellenza tecnica e al buon design migliora l'agilità.
Simplicity–the art of maximizing the amount of work not done–is essential. |  | Einfachheit -- die Kunst, die Menge nicht getaner Arbeit zu maximieren -- ist essenziell. | La simplicité – c’est-à-dire l’art de minimiser la quantité de travail inutile – est essentielle. | Simplicity–the art of maximizing the amount of work not done–is essential. | La semplicità - l'arte di massimizzare la quantità di lavoro non fatto - è essenziale.
The best architectures, requirements, and designs emerge from self-organizing teams. |  | Die besten Architekturen, Anforderungen und Entwürfe entstehen durch selbstorganisierte Teams. | Les meilleures architectures, spécifications et conceptions émergent d'équipes auto-organisées. | The best architectures, requirements, and designs emerge from self-organizing teams. | Le migliori architetture, requisiti e design emergono da team auto-organizzati.
At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly. |  | In regelmäßigen Abständen reflektiert das Team, wie es effektiver werden kann und passt sein Verhalten entsprechend an. | À intervalles réguliers, l'équipe réfléchit aux moyens possibles de devenir plus efficace. Puis elle s'adapte et modifie son fonctionnement en conséquence. | At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly. | A intervalli regolari, il team riflette su come diventare più efficace, poi sintonizza e regola il suo comportamento di conseguenza.
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on D257: Alessandra: falls zu "probabilité" gehörend: weibliche Form

## Projektmgmt
Projet Agile 1
1 | Scrum Master: abc def (abc) |  | Internal res.: | CHF 500 | External res.: | CHF 0 | 0 h / 0 h (Budget)
© iManagement • dr. s.imboden • www.2iManagement.ch | [7 empty] | V. 2.0.0
Protocol of modifications
| Who? | Date |  | Modifications
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
DAILY SCRUM
?
+
-

Vision Scope
Product Backlog
Sprint Planning
Sprint Retrospective
ITERATION
SPRINT
1-4 Weeks
Sprint Review
Sprint Backlog
0/0
Product Increment

## Projektteam
Project team
[39 empty] | abd | abd | [11 empty] | abc def (abd): Budget [h]: 0 / balance budget [h]: 0 / realized [h]: 0
| Project number: | P1 | Start: | [20 empty] | 2026-01-27 |  | Finish: | 2028-02-16 |  | Remarks | [8 empty] | Remarks | ghj | ghj | [11 empty] | ghi jkl (ghj): Budget [h]: 0 / balance budget [h]: 0 / realized [h]: 0 |  | TRUE
| Project title: | Projet Agile 1 | Procuct Owner: | [20 empty] | xyz xxx |  | Scrum Master: | abc def (abc) | [11 empty] | Sc1 | Sc1 | [11 empty] | ScrumTeam 1 1 (Sc1): Budget [h]: 0 / balance budget [h]: 0 / realized [h]: 0
| Department: | see charter | Modified on: | [22 empty] | Deputy: | ghi jkl (ghi) | [12 empty] | T1 (abd) | [11 empty] | T1 (abd) (3)
| Strategic goal: | see charter
[29 empty] | BUDGET | [6 empty] | Realized
21 | Name | First name | Initials | intern | Team | Team | Team | 1 | 2 | 3 | 4 | 5 | Teamleader | [9 empty] | Email |  |  | Telephone | Function | Hourly rate [CHF] | hours budget | allocated hours | BALANCE [h] | [CHF] | Internal resources [CHF] | External resources [CHF] | BALANCE [CHF] | realized hours | [CHF] | Absence/Remarks |  |  | Stunden Team realisiert |  |  |  | Stunden Team verplant
1 | abc | def | abd | x | 1 |  |  |  | 2 | 3 | 4 | 5 | T1 |  |  |  |  | T1 (abd) |  |  |  |  | x.y@hevs.ch |  |  | 123 | Product Owner | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | abc def (abd): Budget [h]: 0 / balance budget [h]: 0 / realized [h]: 0 | abc def (abd) | 1 |  | TRUE
2 | ghi | jkl | ghj |  | 1 |  |  |  | 2 | 3 | 4 | 5 | [10 empty] | abc@def |  |  | 567 | Scrum Master | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ghi jkl (ghj): Budget [h]: 0 / balance budget [h]: 0 / realized [h]: 0 | ghi jkl (ghj) | 0 |  | FALSE
3 | ScrumTeam 1 | 1 | Sc1 |  | 1 |  |  |  | 2 | 3 | 4 | 5 | [14 empty] | Scrum Team | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ScrumTeam 1 1 (Sc1): Budget [h]: 0 / balance budget [h]: 0 / realized [h]: 0 | ScrumTeam 1 1 (Sc1) | 0 |  | FALSE
4 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
5 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
6 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
7 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
8 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
9 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
10 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
11 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
12 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
13 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
14 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
15 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
16 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | T1 (abd) |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
17 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
18 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
19 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
20 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
21 | [7 empty] | 1 | 2 | 3 | 4 | 5 | [16 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 |  | FALSE
22 | [26 empty] | Total intern [CHF] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | T1 (abd) (3)
23 | [26 empty] | Total extern [CHF] |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | (0)
24 | [26 empty] | TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | (0)
© iManagement • dr. s.imboden • www.2iManagement.ch
|  |  | T1 (abd) | T1 (abd) | 3 | 3 | [6 empty] | 1 | 0 | 0 | 0 | 0 | T1 (abd) | Team 2 | Team 3 | Team 4 | Team 5 | 0 | 0 | 1 |  |  |  |  | 0 | [5 empty] | 0 | [12 empty] | (0)
[5 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 2 |  |  |  |  | 0 | [5 empty] | 0 | [12 empty] | (0)
[5 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 3 |  |  |  |  | 0 | [5 empty] | 0
[5 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 4 |  |  |  |  | 0 | [5 empty] | 0
[5 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 5 |  |  |  |  | 0 | [5 empty] | 0
[6 empty] | 0 | [6 empty] | T1 | [9 empty] | 0 |  | 1
[6 empty] | 0 | [6 empty] | 0 | T2 | [8 empty] | 0 |  | 2
[6 empty] | 0 | [6 empty] | 0 | T3 | [8 empty] | 0 |  | 3
[6 empty] | 0 | [6 empty] | 0 | T4 | [8 empty] | 0 |  | 4
[6 empty] | 0 | [6 empty] | 0 | T5 | [8 empty] | 0 |  | 5
[7 empty] | 0 | [17 empty] | 1
[7 empty] | 0 | [17 empty] | 2
[7 empty] | 0 | [17 empty] | 3
[7 empty] | 0 | [17 empty] | 4
[7 empty] | 0 | [17 empty] | 5
?
+
-
Team
Vision/Story
Product Backlog
Sprint Backlog
Sprint Review

## Projektauftrag
Vision/Story
| Project number: |  | P1 | Start: | 2026-01-27 | Finish: |  | 2028-02-16
| Project title: |  | Projet Agile 1 | Procuct Owner: | xyz xxx | Scrum Master: |  | abc def (abc)
| Department: |  |  | Modified on: |  | Deputy: |  | ghi jkl (ghi)
Strategic goal:
What is the vision? What is the story behind this project? Customer Experience?
Im Sinne eines aktiven Content Marketings und zur Bildung einer Community, möchte ich als Kunde eine Podcast Reihe erstellen. Die Marke des Unternehmens soll noch bekannter und stärker werden, was die Firma als ganzes voranbringt. Direkt im Kontakt mit Kunden oder allgemeiner Community zu stehen, schafft eine ander Bindung als lediglich nur im geschäftlichen Umfeld miteinander zu kommunizieren. durch hochwertigen Inhalt soll jeder Zuhörer sich fortbilden können ohne dafür Geld auszugeben. Als ein Nebeneffekt soll durch die gemeinschaftliche Arbeit an dem Podcast das Team gestärkt werden.
Project goals
1. | Bildung einer Community
2. | Stärkung der eigenen Marke | [6 empty] | Indicator 2
3. | Kontaktpunkt von Weiterbildungsmaterial
4. | Teambuiling
5.
6.
Premise / Condition
1. | Die Dauer eines Podcass beträgt max. 30 Minuten
2. | Der Podcast soll auch ohne Video wirken, sodass es auch nur "nebenbei" z.B. im Auto konsumiert werden kann
3. | Das Firmenlogo oder allgemeiner das Corporate Design soll klar im Video zu sehn sein
4. | Drehort des Podcasts ist immer das Office
5. | Der Poscast erscheint jeden Donnerstag
Budget / Resources / Persons
[5 empty] | Plan | Actual state |  | Balance
| Internal resources [CHF] |  |  |  | 500 | 500 | 90 | 0
| External resources [CHF] |  |  |  | 0 | 0 | 0 | 0
| TOTAL RESOURCES |  |  |  | 500 | 500 | 90 | 0
| External financing (eg customers, subsidies etc.) [CHF] |  |  |  | 0 | 0 |  | 0
Deadlines / Milestones (Go/NoGo)
| When? | What? |  |  |  | Who? |  | Approved?
1. | 2026-02-16 |  |  |  |  | abc def (abc) | 2026-02-16 | xyz xxx
2.
3.
4.
5.
6.
7.
8.
Remarks / attachments
1.
2.
3.
4.
5.
| Date |  |  | 2026-01-27
Client signature
Project manager signature
© iManagement • dr. s.imboden • www.2iManagement.ch
?
+
-
Team
Product Backlog
Budget

## Methodik
Roadmap (Projet Agile 1)
© iManagement • dr. s.imboden • www.2iManagement.ch
Phase 1
01
Activité 1
Aktivität 2
...
Résultat 1
Résultat 2
30.11.2022
Ziel/Objectifs
30.12.2022
Phase 2
02
Activité 1
Aktivität 2
...
Résultat 1
Résultat 2
Ziel/Objectifs
Phase 3
03
Activité 1
Aktivität 2
...
Résultat 1
Résultat 2
30.01.2023
Ziel/Objectifs
Activité 1
Aktivität 2
...
Résultat 1
Résultat 2
28.02.2023
Ziel/Objectifs
Phase 4
04
Steps
Activities
Deliverables
Timeline
Goals
Activité 1
Aktivität 2
...
Résultat 1
Résultat 2
30.03.2024
Ziel/Objectifs
Phase 5
05
?
+
-

## Detailplan
Product Backlog
| P1 |  |  | Procuct Owner: xyz xxx
| Projet Agile 1 |  |  | Scrum Master: abc def (abc) | 0/0
#DIV/0!
| No. | Date | EPIC | Story | Sprint | Story points | Start | Period (days) | Finish | Who? | Stage | 0 | [h] | Progress | days
100%
| 1 | 2022-03-05 | Improve Streaming Service for a live feed | iPhone users need access to a vertical view of the live feed when using the mobile app in order to see the whole picture. | 1 | 20 | 2026-01-22 | 14 | 2026-02-04 | T1 | In progress | 2 | 10 | 38.46% | 5/14 | 14 | 5 | 5/14
5 | 2 | 2022-01-01 |  | Desktop users need a “view fullscreen” button in the lower right-hand corner of the video player in order to see the whole picture. | 2 | 25 | 2026-02-05 | 14 | 2026-02-18 | abc | Suspendu | 1 | 5 | 0% | 0/14 | 14 | -9 | -9/14
10 | 3 | 2022-01-02 |  | Android users need to be linked to apple store to find an appropriate app. | 3 | 20 | 2026-02-19 | 14 | 2026-03-04 | ghi | Pas commencé | 1 | 10 | 0% | 0/14 | 14 | -23 | -23/14
| 4 |  |  | Als (Kunde) möchte ich (Ziel/Wunsch) um (Nutzen)
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
© iManagement • dr. s.imboden • www.2iManagement.ch
0/0
?
+
-
+
-
27
AZ
AZ
AZ
AZ
AZ
AZ
Team
Vision/Story
Product Backlog
Sprint Backlog
Sprint Retrospective
Product Increment
Sprint Review
Note on D7: Epics are large bodies of work that can be broken down into a number of smaller tasks (called stories).
Note on E7: Stories, also called “user stories,” are short requirements or requests written from the perspective of an end user.

## SprintBacklog
Sprint Backlog
| P1 |  |  | Procuct Owner: xyz xxx
| Projet Agile 1 |  |  | Scrum Master: abc def (abc) | 0/0
#DIV/0!
| No. | Sprint | Sprint activities | Sprint activities | Release | Budget [h] | Start | Period (days) | Finish | Who? | Stage | 0 | Points | Progress | days
100%
| 1 | 1 |  | iPhone users need access to a vertical view of the live feed when using the mobile app in order to see the whole picture. | R1 | 50 | 2025-12-28 | 14 | 2026-01-10 | ghi | In progress | 2 | 20 | 100% | 30/14 | 14 | 30 | 30/14 | 1 iPhone users need access to a vertical view of the live feed when using the mobile app in order to see the whole picture.
10 | 2 |  |  | Desktop users need a “view fullscreen” button in the lower right-hand corner of the video player in order to see the whole picture. | R2 | 80 | 2026-01-31 | 5 | 2026-02-04 | abc | Pas commencé | 1 | 10 | 0% | 0/5 | 5 | -4 | -4/5 | 2 Desktop users need a “view fullscreen” button in the lower right-hand corner of the video player in order to see the whole picture.
| 3 |  |  | Android users need to be linked to apple store to find an appropriate app. | R3 | 30 | 2026-01-22 | 7 | 2026-01-28 | abc | Suspendu | 3 | 35 | 83.33% | 5/7 | 7 | 5 | 5/7 | 3 Android users need to be linked to apple store to find an appropriate app.
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
© iManagement • dr. s.imboden • www.2iManagement.ch
0/0
?
+
-
+
-
27
AZ
AZ
AZ
AZ
AZ
AZ
Team
Vision/Story
Product Backlog
Sprint Backlog
Sprint Retrospective
Product Increment
Sprint Review

## SprintReview
Sprint Backlog
| P1 | Procuct Owner: xyz xxx | Modified on: | 2022-01-01
| Projet Agile 1 | Scrum Master: abc def (abc)
| EPIC | Improve Streaming Service for a live feed
| Target | To Do | In progress | Accomplished | Remarks/Lessons Learned
1 | 1 iPhone users need access to a vertical view of the live feed when using the mobile app in order to see the whole picture.
2 | 1.1 Desktop users need a “view fullscreen” button in the lower right-hand corner of the video player in order to see the whole picture.
3 | Target 3
4
© iManagement • dr. s.imboden • www.2iManagement.ch
?
+
-
+
-
27
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Task 2
Task 1
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Dies ist ein Text
Team
Vision/Story
Product Backlog
Sprint Backlog
Sprint Retrospective
Product Increment
Sprint Review

## SprintRetrospective
Sprint Retrospective
| Project number: | P1 | Start: | 46049 | 2026-01-27 |  | Finish: |  | 2028-02-16 | 3 | grün | 30%
| Project title: | Projet Agile 1 | Procuct Owner: |  | xyz xxx |  | Scrum Master: |  | abc def (abc) | 1 | orange | 30%
| Department: | see charter | Modified on: |  |  |  | Deputy: |  | ghi jkl (ghi) | 0 | rot | 50%
| Sprint: | 1 As an employee I want so search for other employees using their last name so that I can easliy contact any colleague. | [8 empty] | 87.5%
General Evaluation (1 = proceeding according to plan, 2 = be watchful = 3 critical)
[11 empty] | Wert | 87.5%
| Overall sprint | According to plan | 1 | [7 empty] | Breite | 0.3%
| Budget/Resources | Be watchful | 2 | [7 empty] | Ende | 112.2%
| Quality/Goals | According to plan | 1
| Deadlines/Planning | According to plan | 1
Remarks
| Sprint goals | [7 empty] | In %
1. | 1 iPhone users need access to a vertical view of the live feed when using the mobile app in order to see the whole picture. | [7 empty] | 50%
2. | 1.1 Desktop users need a “view fullscreen” button in the lower right-hand corner of the video player in order to see the whole picture. | [7 empty] | 30%
3. | Target 3
4.
Achievements (last period)
1.
2.
3.
4.
5.
6.
Particular problems (last period)
1.
2.
3.
4.
5.
Challenges (next period)
1.
2.
3.
4.
0 | Next milestone:
Budget / Resources / Persons
[5 empty] | Plan |  | Actual state |  | Balance
| Internal resources [CHF] |  |  |  | 500 |  | 500 | 80 | 0
| External resources [CHF] |  |  |  | 0 | 0 | 0 | 0 | 0
| TOTAL RESOURCES |  |  |  | 500 | 500 | 500 | 80 | 0
| External financing (eg customers, subsidies etc.) |  |  |  | 0 |  | 0 |  | 0
Remarks / attachments
© iManagement • dr. s.imboden • www.2iManagement.ch
?
+
-
Product Backlog
Sprint Backlog
Sprint Review

## Projektabschluss
Product Increment
| Project number: | P1 | Start: | 46049 | 2026-01-27 |  | Finish: |  | 2028-02-16
| Project title: | Projet Agile 1 | Procuct Owner: |  | xyz xxx |  | Scrum Master: |  | abc def (abc)
| Department: | see charter | Modified on: |  |  |  | Deputy: |  | ghi jkl (ghi)
| Sprint: | 1 iPhone users need access to a vertical view of the live feed when using the mobile app in order to see the whole picture.
| Is the (partial) product successful? |  | Yes |  | 1
Reason:
| Are all customer needs satisfied? |  | Yes |  | 1
Reason:
| Was the budget observed? |  | Yes |  | 1
[5 empty] | Plan |  | Actual state |  | Balance
| Internal resources [CHF] |  |  |  | 500 |  | 500 | 80 | 0
| External resources [CHF] |  |  |  | 0 | 0 | 0 | 0 | 0
| TOTAL RESOURCES |  |  |  | 500 | 500 | 500 | 80 | 0
| External financing (eg customers, subsidies etc.) |  |  |  | 0 |  | 0 |  | 0
Reason:
What can be learnt from the project? (Lessons Learned)
1.
2.
3.
4.
5.
6.
Remarks / attachments
| Date |  | 2028-02-16
Client signature
Project manager signature
© iManagement • dr. s.imboden • www.2iManagement.ch
?
+
-
Product Backlog
Sprint Backlog
Sprint Review

## Projektbudget
0 |  |  |  | B U D G E T | (Projet Agile 1)
x!A571
|  |  | Internal resources |  |  | Plan [CHF] | Actual state [CHF] | Balance [CHF] | Remarks
|  | 1 | Personnel resources (internal) |  |  | 0 | 0 | 0 | Compare detail project team
|  | 2 |  |  |  | 500 | 500 | 0
|  | 3 |  |  |  | 0 | 0 | 0
|  | 4 |  |  |  | 0 | 0 | 0
|  | 5 |  |  |  | 0 | 0 | 0
|  | 6 |  |  |  | 0 | 0 | 0
|  | 7 |  |  |  | 0 | 0 | 0
|  | 8 |  |  |  | 0 | 0 | 0
|  | 9 |  |  |  | 0 | 0 | 0
|  | 10 |  |  |  | 0 | 0 | 0
|  | 11 |  |  |  | 0 | 0 | 0
|  | 12 |  |  |  | 0 | 0 | 0
|  | 13 |  |  |  | 0 | 0 | 0
|  | 14 |  |  |  | 0 | 0 | 0
|  | 15 |  |  |  | 0 | 0 | 0
|  | 16 |  |  |  | 0 | 0 | 0
|  | 17 |  |  |  | 0 | 0 | 0
|  | 18 | TOTAL internal resources |  |  | 500 | 500 | 0 | 100%
|  |  | External resources |  |  | Plan [CHF] | Actual state [CHF] | Balance [CHF] | Remarks
[6 empty] | 0 | 2 | 0 | 0
|  | 1 | Personnel resources (external) |  |  | 0 | 0 | 0
|  | 2 |  |  |  |  | 0 | 0
|  | 3 |  |  |  | 0 | 0 | 0
|  | 4 |  |  |  | 0 | 0 | 0
|  | 5 |  |  |  | 0 | 0 | 0
|  | 6 |  |  |  | 0 | 0 | 0
|  | 7 |  |  |  | 0 | 0 | 0
|  | 8 |  |  |  | 0 | 0 | 0
|  | 9 |  |  |  | 0 | 0 | 0
|  | 10 |  |  |  | 0 | 0 | 0
|  | 11 |  |  |  | 0 | 0 | 0
|  | 12 |  |  |  | 0 | 0 | 0
|  | 13 |  |  |  | 0 | 0 | 0
|  | 14 |  |  |  | 0 | 0 | 0
|  | 15 |  |  |  | 0 | 0 | 0
|  | 16 |  |  |  | 0 | 0 | 0
|  | 17 |  |  |  | 0 | 0 | 0
|  | 18 |  |  |  | 0 | 0 | 0
|  | 19 |  |  |  | 0 | 0 | 0
|  | 20 |  |  |  | 0 | 0 | 0
|  | 21 |  |  |  | 0 | 0 | 0
|  | 22 |  |  |  | 0 | 0 | 0
|  | 23 |  |  |  | 0 | 0 | 0
|  | 24 |  |  |  | 0 | 0 | 0
|  | 25 |  |  |  | 0 | 0 | 0
|  | 26 |  |  |  | 0 | 0 | 0
|  | 27 |  |  |  | 0 | 0 | 0
|  | 28 |  |  |  | 0 | 0 | 0
|  | 29 |  |  |  | 0 | 0 | 0
|  | 30 | TOTAL external resources [CHF] |  |  | 0 | 0 | 0 | 0%
|  | 23 | TOTAL RESOURCES |  |  | 500 | 500 | 0 | 100%
|  |  | External financing |  |  | Plan [CHF] | Actual state [CHF] | Balance [CHF] | Remarks
[6 empty] | 0 | 2 | 0 | 0
|  | 1 |  |  |  |  | 0 | 0 | External financing (eg customers, subsidies etc.)
|  | 2 |  |  |  | 0 | 0 | 0
|  | 3 |  |  |  | 0 | 0 | 0
|  | 4 |  |  |  | 0 | 0 | 0
|  | 5 |  |  |  | 0 | 0 | 0
|  | 6 |  |  |  | 0 | 0 | 0
|  | 7 |  |  |  | 0 | 0 | 0
|  | 8 |  |  |  | 0 | 0 | 0
|  | 9 |  |  |  | 0 | 0 | 0
|  | 10 |  |  |  | 0 | 0 | 0
|  | 11 | TOTAL external finances |  |  | 0 | 0 | 0 | 0%
© iManagement • dr. s.imboden • www.2iManagement.ch
?
+
-
Team
Vision/Story
Product Backlog
Sprint Backlog
Sprint Retrospective
Product Increment

## Stakeholder
S T A K E H O L D E R
No. | Stakeholder | Extent of interests | Degree of influence | Interests, expectations | Size of group | Chances (+) and dangers (-) | Possible measures | Status
s1 | Team | 3 | 7 |  | 1 |  |  | 1 | 1
s2 | Groupe 2 | 8 | 9 |  | 2 |  |  | 1 | 2
s3 | Gruppe 3 | 7 | 5 |  | 3 |  |  |  | 3
s4 | Groupe 4 | 1 | 2 | [5 empty] | 1
s5 | [8 empty] | 1
s6 | [8 empty] | 1
s7 | [8 empty] | 1
s8 | [8 empty] | 1
s9 | [8 empty] | 1
s10 | [8 empty] | 1
s11 | [8 empty] | 1
s12 | [8 empty] | 1
s13 | [8 empty] | 1
s14 | [8 empty] | 1
s15 | [8 empty] | 1
s16 | [8 empty] | 1
s17 | [8 empty] | 1
s18 | [8 empty] | 1
s19 | [8 empty] | 1
s20 | [8 empty] | 1
© iManagement • dr. s.imboden • www.2iManagement.ch
s1 Team
s2 Groupe 2
s3 Gruppe 3
s4 Groupe 4
Copy arrow: ctrl and left mouse button
Frequent contacts
Regular contacts
Rare contacts
© iManagement • dr. s.imboden • www.2iManagement.ch
Stakeholder influence
Stakeholder interest
High
Low
Big
Small
Immediate environment
Groupe 4
Groupe 2
Gruppe 3
Team
Wider environment
Internal
Manage closely
Us
Keep satisfied
Monitor
Keep informed
?
Team
Vision/Story
Product Backlog
Sprint Backlog

## Projektcontrolling
P R O J E C T C O N T R O L L I N G
1 | No. | Projects | Prio | Who? | Start | Finish | In % |  | Remarks
| p1 | Project 1 | 1 | uvw xyz (xyz) | 2014-01-01 | 2014-12-31 | 50% | 3
| p2 |  | 2 |  |  |  |  | 2
| p3 |  | 3
p4
p5
p6
p7
p8
p9
p10
p11
p12
p13
p14
p15
p16
p17
p18
p19
p20
p21
p22
p23
p24
p25
p26
p27
p28
p29
p30
p31
p32
p33
p34
p35
p36
p37
p38
p39
p40
p41
p42
p43
p44
p45
p46
p47
p48
p49
p50
p51
p52
p53
p54
p55
p56
p57
p58
p59
p60
p61
p62
p63
p64
p65
p66
p67
p68
p69
p70
p71
p72
p73
p74
p75
p76
p77
p78
p79
p80
p81
p82
p83
p84
© iManagement • dr. s.imboden • www.2iManagement.ch
+
-
?


## Kommunikation
C O M M U N I C A T I O N
No. | Goals | No. | Target public | Key Message | Channel | Periodicity | Prio | Who? | Start | Finish | ok
1 | Tenir informé | p1 | Team | Informations sur les décisions | eMail | hebdomadaire | 1 | abc | 2026-01-27 | 2028-02-16 | 1
|  | p2 | Partenaires clé | Actualité du mois | newslettre | mensuel | 2 | ghi | 2019-01-01 | 2028-02-26 | 2
p3
p4
p5
p6
p7
p8
2 |  | p9
p10
p11
p12
p13
p14
p15
p16
3 |  | p17
p18
p19
p20
p21
p22
p23
p24
4 |  | p25
p26
p27
p28
p29
p30
p31
p32
5 |  | p33
p34
p35
p36
p37
p38
p39
p40
6 |  | p41
p42
p43
p44
p45
p46
p47
p48
7 |  | p49
p50
p51
p52
p53
p54
p55
p56
8 |  | p57
p58
p59
p60
p61
p62
p63
p64
9 |  | p65
p66
p67
p68
p69
p70
p71
p72
10 |  | p73
p74
p75
p76
p77
p78
p79
p80
© iManagement • dr. s.imboden • www.2iManagement.ch
+
-
?
Team
Vision/Story
Product Backlog
Sprint Backlog

## Swot-Analyse
S W O T A N A L Y S I S
| Strength |  | 5 | 4 | 3 | 2 | 1 | -1 | -2 | -3 | -4 | -5 |  | Weaknesses
s1 |  | 1 |  |  |  |  | ❶ |  |  |  | ❹ |  | w1 |  | -4
s2 |  | 3 |  |  | ❸ |  |  |  | ❷ |  |  |  | w2 |  | -2
s3 | [12 empty] | w3
s4 | [12 empty] | w4
s5 | [12 empty] | w5
s6 | [12 empty] | w6
s7 | [12 empty] | w7
s8 | [12 empty] | w8
s9 | [12 empty] | w9
s10 | [12 empty] | w10
s11 | [12 empty] | w11
s12 | [12 empty] | w12
s13 | [12 empty] | w13
s14 | [12 empty] | w14
s15 | [12 empty] | w15
s16 | [12 empty] | w16
s17 | [12 empty] | w17
s18 | [12 empty] | w18
s19 | [12 empty] | w19
s20 | [12 empty] | w20
| Opportunities | 4 | 5 | 4 | 3 | 2 | 1 | -1 | -2 | -3 | -4 | -5 |  | Threats | 6
o1 |  | 1 |  |  |  |  | ❶ | ❶ |  |  |  |  | t1 |  | -1
o2 |  | 3 |  |  | ❸ | [5 empty] | ❹ |  | t2 |  | -4
o3 | [12 empty] | t3
o4 | [12 empty] | t4
o5 | [12 empty] | t5
o6 | [12 empty] | t6
o7 | [12 empty] | t7
o8 | [12 empty] | t8
o9 | [12 empty] | t9
o10 | [12 empty] | t10
o11 | [12 empty] | t11
o12 | [12 empty] | t12
o13 | [12 empty] | t13
o14 | [12 empty] | t14
o15 | [12 empty] | t15
o16 | [12 empty] | t16
o17 | [12 empty] | t17
o18 | [12 empty] | t18
o19 | [12 empty] | t19
o20 | [12 empty] | t20
© iManagement • dr. s.imboden • www.2iManagement.ch |  | 4 | [12 empty] | 5
[14 empty] | Strength | 4
[14 empty] | Threats | 5
[14 empty] | Weaknesses | 6
[14 empty] | Opportunities | 4
© iManagement • dr. s.imboden • www.2iManagement.ch
?
+
-
Team
Vision/Story
Product Backlog
Sprint Backlog

## Risikomgmt
R I S K A N A L Y S I S
No. | Risk | Extent of damage | Probability of occurrence | Consequences | Ten-dency | Possible measures | Status
R1 | Risque 1 | 2 | 9 |  | 1 |  | 2 | 1
R2 | Risque 2 | 5 | 5 |  |  |  |  | 1
R3 | [7 empty] | 1
R4 | [7 empty] | 1
R5 | [7 empty] | 1
R6 | [7 empty] | 1
R7 | [7 empty] | 1
R8 | [7 empty] | 1
R9 | [7 empty] | 1
R10 | [7 empty] | 1
R11 | [7 empty] | 1
R12 | [7 empty] | 1
R13 | [7 empty] | 1
R14 | [7 empty] | 1
R15 | [7 empty] | 1
© iManagement • dr. s.imboden • www.2iManagement.ch
Probability of occurrence
Extent of damage
High
Low
High
Low
Medium
Medium
Aucune action nécessaire
Action nécessaire
Action urgente
+
-
?
Team
Vision/Story
Product Backlog
Sprint Backlog

## Machbarkeit
F E A S I B I L I T Y (Projet Agile 1)
|  |  |  | Organizational feasibility | 7
|  |  |  | Technical feasibility | 3
|  |  |  | Legal feasibility | 3
|  |  |  | Economic feasibility | 1
|  |  |  | Resources and time | 4
Organizational feasibility
No. | Title | Consequences | Influence on the project | Degree of danger | Ten-dency | Possible measures | Status | 1
1 |  |  | 3 |  | 2 |  | 1 | 0
2 |  |  | 4 |  | 3 |  | 3 | 1
3
4
5
6
7
8
9
10
|  | Sum | 7
Technical feasibility
No. | Title | Consequences | Influence on the project | Degree of danger | Ten-dency | Possible measures | Status | 1
1 |  |  | 3 |  |  |  | 1 | 0
2 | [7 empty] | 0
3
4
5
6
7
8
9
10
|  | Sum | 3
Legal feasibility
No. | Title | Consequences | Influence on the project | Degree of danger | Ten-dency | Possible measures | Status | 0
1 |  |  | 3 |  | 1 |  | 3 | 0
2 | [7 empty] | 1
3
4
5
6
7
8
9
10
|  | Sum | 3
Economic feasibility
No. | Title | Consequences | Influence on the project | Degree of danger | Ten-dency | Possible measures | Status | 0
1 |  |  | 1 |  | 1 |  | 3 | 0
2 | [7 empty] | 1
3
4
5
6
7
8
9
10
|  | Sum | 1
Resources and time
No. | Title | Consequences | Influence on the project | Degree of danger | Ten-dency | Possible measures | Status | 0
1 |  |  | 4 |  | 2 |  |  | 0
2 | [7 empty] | 0
3
4
5
6
7
8
9
10
© iManagement • www.2iManagement.ch |  | Sum | 4
Organizational feasibility
1
0
1
Economic feasibility
0
0
1
Technical feasibility
1
0
0
Legal feasibility
0
0
1
Resources and time
0
0
0
+
-
?
Stakeholder
SWOT
Risks
COM
Vision/Story
Product Backlog
Sprint Backlog
Note on F24: min. 0 max. 3
Note on I69: 1=grün 2=orange 3=rot

## Kalender
Calendar
2026
[22 empty] | Jahr | 2026
2026-01-01 | [6 empty] | 2026-02-01 | [7 empty] | 2026-03-01 | [6 empty] | Mois | 1
Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su |  | Mo | Tu | We | Th | Fr | Sa | Su | Jour début | 2 | (1 = dimanche, 2 = lundi, ...)
|  |  | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | [6 empty] | 2026-02-01 | [7 empty] | 2026-03-01 | [6 empty] | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | [6 empty] | 2026-02-01 | [6 empty] | 2026-03-01
2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 |  | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 |  |  |  | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-02-02 | 2026-02-03 | 2026-02-04 | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08
2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 |  | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 |  |  |  | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15
2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 |  | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 |  |  |  | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22
2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 |  | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 |  |  | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 |  |  |  | 2026-01-26 | 2026-01-27 | 2026-01-28 | 2026-01-29 | 2026-01-30 | 2026-01-31 |  | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 |  | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29
[15 empty] | 2026-03-30 | 2026-03-31 | [22 empty] | 2026-03-30 | 2026-03-31
2026-04-01 | [6 empty] | 2026-05-01 | [7 empty] | 2026-06-01
Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su |  | Mo | Tu | We | Th | Fr | Sa | Su
|  | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 |  |  |  |  | 2026-05-01 | 2026-05-02 | 2026-05-03 |  | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | [5 empty] | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 |  |  |  |  | 2026-05-01 | 2026-05-02 | 2026-05-03 | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07
2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 |  | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 |  |  |  | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-05-04 | 2026-05-05 | 2026-05-06 | 2026-05-07 | 2026-05-08 | 2026-05-09 | 2026-05-10 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14
2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 |  | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 |  |  |  | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-05-11 | 2026-05-12 | 2026-05-13 | 2026-05-14 | 2026-05-15 | 2026-05-16 | 2026-05-17 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21
2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 |  | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28 |  |  |  | 2026-04-20 | 2026-04-21 | 2026-04-22 | 2026-04-23 | 2026-04-24 | 2026-04-25 | 2026-04-26 | 2026-05-18 | 2026-05-19 | 2026-05-20 | 2026-05-21 | 2026-05-22 | 2026-05-23 | 2026-05-24 | 2026-06-22 | 2026-06-23 | 2026-06-24 | 2026-06-25 | 2026-06-26 | 2026-06-27 | 2026-06-28
2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 |  |  |  | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 |  | 2026-06-29 | 2026-06-30 | [8 empty] | 2026-04-27 | 2026-04-28 | 2026-04-29 | 2026-04-30 |  |  |  | 2026-05-25 | 2026-05-26 | 2026-05-27 | 2026-05-28 | 2026-05-29 | 2026-05-30 | 2026-05-31 | 2026-06-29 | 2026-06-30
2026-07-01 | [6 empty] | 2026-08-01 | [7 empty] | 2026-09-01
Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su |  | Mo | Tu | We | Th | Fr | Sa | Su
|  | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | [5 empty] | 2026-08-01 | 2026-08-02 |  |  | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06 | [5 empty] | 2026-07-01 | 2026-07-02 | 2026-07-03 | 2026-07-04 | 2026-07-05 | [5 empty] | 2026-08-01 | 2026-08-02 |  | 2026-09-01 | 2026-09-02 | 2026-09-03 | 2026-09-04 | 2026-09-05 | 2026-09-06
2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 |  | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13 |  |  |  | 2026-07-06 | 2026-07-07 | 2026-07-08 | 2026-07-09 | 2026-07-10 | 2026-07-11 | 2026-07-12 | 2026-08-03 | 2026-08-04 | 2026-08-05 | 2026-08-06 | 2026-08-07 | 2026-08-08 | 2026-08-09 | 2026-09-07 | 2026-09-08 | 2026-09-09 | 2026-09-10 | 2026-09-11 | 2026-09-12 | 2026-09-13
2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 |  | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20 |  |  |  | 2026-07-13 | 2026-07-14 | 2026-07-15 | 2026-07-16 | 2026-07-17 | 2026-07-18 | 2026-07-19 | 2026-08-10 | 2026-08-11 | 2026-08-12 | 2026-08-13 | 2026-08-14 | 2026-08-15 | 2026-08-16 | 2026-09-14 | 2026-09-15 | 2026-09-16 | 2026-09-17 | 2026-09-18 | 2026-09-19 | 2026-09-20
2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 |  | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 |  |  |  | 2026-07-20 | 2026-07-21 | 2026-07-22 | 2026-07-23 | 2026-07-24 | 2026-07-25 | 2026-07-26 | 2026-08-17 | 2026-08-18 | 2026-08-19 | 2026-08-20 | 2026-08-21 | 2026-08-22 | 2026-08-23 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27
2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 |  | 2026-09-28 | 2026-09-29 | 2026-09-30 | [7 empty] | 2026-07-27 | 2026-07-28 | 2026-07-29 | 2026-07-30 | 2026-07-31 |  |  | 2026-08-24 | 2026-08-25 | 2026-08-26 | 2026-08-27 | 2026-08-28 | 2026-08-29 | 2026-08-30 | 2026-09-28 | 2026-09-29 | 2026-09-30
[7 empty] | 2026-08-31 | [24 empty] | 2026-08-31
2026-10-01 | [6 empty] | 2026-11-01 | [7 empty] | 2026-12-01
Mo | Tu | We | Th | Fr | Sa | Su | Mo | Tu | We | Th | Fr | Sa | Su |  | Mo | Tu | We | Th | Fr | Sa | Su
|  |  | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | [6 empty] | 2026-11-01 |  |  | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06 | [6 empty] | 2026-10-01 | 2026-10-02 | 2026-10-03 | 2026-10-04 | [6 empty] | 2026-11-01 |  | 2026-12-01 | 2026-12-02 | 2026-12-03 | 2026-12-04 | 2026-12-05 | 2026-12-06
2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 |  | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13 |  |  |  | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05 | 2026-11-06 | 2026-11-07 | 2026-11-08 | 2026-12-07 | 2026-12-08 | 2026-12-09 | 2026-12-10 | 2026-12-11 | 2026-12-12 | 2026-12-13
2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 |  | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20 |  |  |  | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-11-09 | 2026-11-10 | 2026-11-11 | 2026-11-12 | 2026-11-13 | 2026-11-14 | 2026-11-15 | 2026-12-14 | 2026-12-15 | 2026-12-16 | 2026-12-17 | 2026-12-18 | 2026-12-19 | 2026-12-20
2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 |  | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27 |  |  |  | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-11-16 | 2026-11-17 | 2026-11-18 | 2026-11-19 | 2026-11-20 | 2026-11-21 | 2026-11-22 | 2026-12-21 | 2026-12-22 | 2026-12-23 | 2026-12-24 | 2026-12-25 | 2026-12-26 | 2026-12-27
2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 |  | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 |  | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31 | [6 empty] | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 |  | 2026-11-23 | 2026-11-24 | 2026-11-25 | 2026-11-26 | 2026-11-27 | 2026-11-28 | 2026-11-29 | 2026-12-28 | 2026-12-29 | 2026-12-30 | 2026-12-31
[7 empty] | 2026-11-30 | [6 empty] | [42] | [17 empty] | 2026-11-30
© iManagement • dr. s.imboden • www.2iManagement.ch

## Logo
Agile Manifesto
Your logo:
We are uncovering better ways of developing software by doing it and helping others do it. Through this work we have come to value:
[6 empty] | Individuals and interactions | over processes and tools
[6 empty] | Working software | over comprehensive documentation
Currency: | CHF | CHF? h? |  |  |  | Customer collaboration | over contract negotiation
[6 empty] | Responding to change | over following a plan
red | 50% |  | Wert | 50%
orange | 30% |  | Breite | 0.3% |  | That is, while there is value in the items on the right, we value the items on the left more.
green | 20% |  | Ende | 149.7%
Leer | 100%
TOTAL | 100%
[6 empty] | Our highest priority is to satisfy the customer through early and continuous delivery of valuable software. | Working software is the primary measure of progress.
Stage
Not started
In progress | [5 empty] | Welcome changing requirements, even late in development. Agile processes harness change for the customer’s competitive advantage. | Agile processes promote sustainable development. The sponsors, developers, and users should be able to maintain a constant pace indefinitely.
Stopped
Testing
Completed
Accepted | [5 empty] | Deliver working software frequently, from a couple of weeks to a couple of months, with a preference to the shorter timescale. | Continuous attention to technical excellence and good design enhances agility.
© iManagement • dr. s.imboden • www.2iManagement.ch
[6 empty] | Business people and developers must work together daily throughout the project. | Simplicity–the art of maximizing the amount of work not done–is essential.
[6 empty] | Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done. | The best architectures, requirements, and designs emerge from self-organizing teams.
[6 empty] | The most efficient and effective method of conveying information to and within a development team is face-to-face conversation. | At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly.
2001 : Kent Beck, Ward Cunningham, Dave Thomas, Jeff Sutherland, Ken Schwaber, Jim Highsmith, Alistair Cockburn, Robert C. Martin, Mike Beedle, Arie van Bennekum, Martin Fowler, James Grenning, Andrew Hunt , Ron Jeffries, Jon Kern, Brian Marick, Steve Mellor.
?

1
2
3
4
5
6
7
8
9
10
11
12